| MINISTRY OF SCIENCE AND TECHNOLOGY NATIONAL OFFICE IN SOUTHERN REGION CENTER FOR SCIENCE AND TECHNOLOGY APPLICATION AND SERVICES | VIETNAM UNION OF SCIENCE AND TECHNOLOGY ASSOCIATIONS VIETBRAND CENTER FOR RESEARCH AND DEVELOPMENT |
| --- | --- |

THE PLAN FOR

PROGRAM ON INVESTMENT MATCHING AND TECHNOLOGICAL TRANSFER

SCIENCE AND TECHNOLOGY FOR AGRICULTURAL DEVELOPMENT IN

SOUTH CENTRAL COAST AND CENTRAL HIGHLANDS 2018

According to the content of the Program on “Science and Technology for Agricultural Development in South Central Coast and Central Highlands 2018” no. 3568-PTTTDN approved on 31 May 2017 by the Ministry of Science and Technology, the National Agency for Technology Entrepreneurship and Commercialization Development, a function unit of the Ministry of Science and Technology, and Vietbrand Center for Research and Development together organize the Program on “Investment Matching and Technological Transfer”.

The Vietbrand Center for Research Development kindly proposes the Plan for the Program on “Investment Matching and Technological Transfer” as follows:

- OBJECTIVES:

- Executing the detailed introduction of supply and demand of local and foreign businesses, cooperatives, etc.

- Grasping the needs of municipal and provincial businesses; assisting businesses in technological innovation and transfer as well as scientific and technological application for production, processing and preservation of agricultural products.

- Directly linking to prestigious suppliers, experts and consultants so that all business can receive good preference.

- SCOPE OF TASKS:

- The following is the specific steps for the Program on “Investment Matching and Technological Transfer”:

- Surveying the demand for technology and equipment from all businesses of this Program;

- Gathering, screening, finishing and sending all information to the suppliers and experts for the preparation of consultancy documentation;

- Organizing and introducing the supply-demand matching to local and foreign businesses.

- Key tasks:

      - Preparing introduction dossiers: Preparing a set of dossiers, including:

  - List of businesses that have registered the demand for technology and equipment.

  - Municipal and provincial Department of Science and Technology and Department of Agriculture and Rural Development;

  - Agricultural business associations;

  - Municipal and provincial businesses.

  - Registration form.

  - List of offered technology and equipment (priority is given to the technology and equipment displayed at the exhibition center of the Program on “Science and Technology for Agricultural Development in South Central Coast and Central Highlands 2018”).

- Sending plan details to all cities/provinces: Enclosing the official letters of governmental bodies, registration forms and list of offered technology and equipment.

- Collecting feedbacks of businesses from demand survey: Giving instructions for conducting the survey and collecting feedbacks of businesses.

- Gathering and screening all information of technology and equipment required for consultancy: Preparing all documents regarding technology and equipment required for consultancy at the event.

- Setting up a consultancy schedule: Contacting businesses and experts to agree to a consultancy schedule.

- Organizing the Program on “Investment Matching and Technological Transfer”: Arranging consultancy and signing places for businesses and experts.

- Summarizing results: Building up a file on such results for post-event matching.

- PERFORMANCE SCHEDULE:

| No | Description | Performed by | Time |
| --- | --- | --- | --- |
| 1 | Sending invitations for the supply – demand matching: equipment, technology and product to be transferred for market development (supply and demand registration forms). | Vietbrand Center; Khanh Hoa Department of Science and Technology; Center for Science and Technology Application and Services | 5 March – 20 April 2018 |
| 2 | Updating supply registration; gathering and providing all information of technology, equipment and product (seller) to the Organization Board. Introduction details should be made in Vietnamese and English. | Local departments and agencies; local businesses; individuals; Vietbrand Center | 2 – 23 April 2018 |
| 3 | Collecting and screening the supply information | Vietbrand Center; Khanh Hoa Department of Science and Technology; Center for Science and Technology Application and Services | 9 – 27 April 2018 |
| 4 | Updating demand registration; gathering and providing all information of technology, equipment and product (buyer) | Local departments and agencies; local businesses; individuals; Vietbrand Center; Center for Science and Technology Application and Services | 2 – 23 April 2018 |
| 5 | Collecting and screening the demand information | Vietbrand Center; Center for Science and Technology Application and Services | 9 – 27 April 2018 |
| 6 | Conducting preliminary consultancy; considering feedbacks from demand survey for technology and equipment; collecting and screening all information of technology, equipment and product in compliance with the needs of businesses and individuals. Setting up and confirming consultancy and signing schedules for the Program. | Vietbrand Center; Center for Science and Technology Application and Services | 1 – 25 April 2018 |
| 7 | Designing the Program and decorating the place for organizing the Program. Checking and finishing the design and decoration. | Vietbrand Center; Center for Science and Technology Application and Services | 7 – 27 June 2018 |
| 8 | Organizing the Program. | Vietbrand Center; Center for Science and Technology Application and Services | 28 June – 2 July 2018 |
| 9 | Summarizing the results of the supply – demand matching | Vietbrand Center; Center for Science and Technology Application and Services | 7 – 15 May 2018 |

- COST ESTIMATION:

All expenses for the Program on “Investment Matching and Technological Transfer” are mobilized by the Organization Board from the socialized expense sources of the Program on “Science and Technology for Agricultural Development in South Central Coast and Central Highlands 2018”.

The foregoing is the Plan for the Program on “Investment Matching and Technological Transfer”, part of the Program on “Science and Technology for Agricultural Development in South Central Coast and Central Highlands 2018”. The Organization Board sincerely requests local departments, agencies and businesses to maintain close coordination for the success of the Program.

Faithfully yours,

THE ORGANIZATION BOARD